## BlackBaud
Cost
Description | Implementation 2022 | Year 2023 | Year 2024 | Year 2025 | Year 2026
Rackspace Hosting Cost | 3000 | 3000 | 3000 | 3000 | 3000
Web Development Cost | 5000
Site Maintenance Cost |  | 1500 | 1500 | 1500 | 1500
BlackBaud Consultant Cost | 50000
Testing Cost by Credit Card Company | 1000
Training Cost for 27 Staffs (Assuming $60 training cost for each staff) | 1620
System Downtime Cost (while integration) | 4300
Interest Cost ( Assuming company take loan of $60,000 from bank @3% per annum for 4 years) |  | 936.75 | 936.75 | 936.75 | 936.75
Total Cost | 64920 | 5436.75 | 5436.75 | 5436.75 | 5436.75
Benefits | [5 empty] | Cost saving calculation for Summer and Non Summer Months: Credit card fees are charged at lowest 1.2% because of all POS integrations and valume of sales is greater than $80,000 per month round the year
(Assuming Customers spending increases 1% each year in all facilities) | [5 empty] | Non Summer Months(Assuming 9 months)
Gate and Membership credit card fees savings | 4080 | 4120.8 | 4162.008 | 4203.6281 | 4245.6644 | Gate and Membership credit card fees savings | 3960
Café credit card fees savings | 4263 | 4305.63 | 4348.6863 | 4392.1732 | 4436.0949 | Café credit card fees savings | 2871
Store credit card fees savings | 4446 | 4490.46 | 4535.3646 | 4580.7182 | 4626.5254 | Store credit card fees savings | 3762
Events credit card fees savings | 3630 | 3666.3 | 3702.963 | 3739.9926 | 3777.3926 | Events credit card fees savings | 2178
Cost savings from office staff taking manual calls (40 hours per week) (Assusimg staffs are paid @$15/hour and it increases 3% annually) | 31200 | 32136 | 33100.08 | 34093.0824 | 35115.8749 | Summer Months(Assuming 3 months of summer)
Total Benefits | 47619 | 48719.19 | 49849.1019 | 51009.5945 | 52201.5521 | Gate and Membership credit card fees savings | 120
[6 empty] | Café credit card fees savings | 1392
ROI | 187.8% |  |  |  |  | Store credit card fees savings | 684
Payback Year | 2 |  |  |  |  | Events credit card fees savings | 1452

## Independent Consultant-BB
Cost
Description | Implementation 2022 | Year 2023 | Year 2024 | Year 2025 | Year 2026
Rackspace Hosting Cost | 3000 | 3000 | 3000 | 3000 | 3000
Web Development Cost | 5000
Site Maintenance Cost |  | 1500 | 1500 | 1500 | 1500
Independent Consultant Cost | 35000
System Integration Issues fixing cost | 10000
Testing Cost by Credit Card Company | 1000
Training Cost for Staffs (Assuming $60 training cost for each staff) | 1620
System Downtime Cost (while integration) | 4300
Interest Cost ( Assuming company take loan of $60,000 from bank @3% per annum for 4 years) |  | 936.75 | 936.75 | 936.75 | 936.75
Total Cost | 59920 | 5436.75 | 5436.75 | 5436.75 | 5436.75
Benefits
(Assuming Customers spending increases 1% each year in all facilities)
Gate and Membership credit card fees savings | 4080 | 4120.8 | 4162.008 | 4203.6281 | 4245.6644
Café credit card fees savings | 4263 | 4305.63 | 4348.6863 | 4392.1732 | 4436.0949
Store credit card fees savings | 4446 | 4490.46 | 4535.3646 | 4580.7182 | 4626.5254
Events credit card fees savings | 3630 | 3666.3 | 3702.963 | 3739.9926 | 3777.3926
Cost savings from office staff taking manual calls (40 hours per week) (Assusimg staffs are paid @$15/hour and it increases 3% annually) | 31200 | 32136 | 33100.08 | 34093.0824 | 35115.8749
Total Benefits | 47619 | 48719.19 | 49849.1019 | 51009.5945 | 52201.5521
ROI | 205.4%
Payback Year | 2

## Independent Consultant-Kindful
Cost
Description | Implementation 2022 | Year 2023 | Year 2024 | Year 2025 | Year 2026
Rackspace Hosting Cost | 3000 | 3000 | 3000 | 3000 | 3000
Web Development Cost | 5000
Site Maintenance Cost |  | 1500 | 1500 | 1500 | 1500
Independent Consultant Cost | 35000
System Integration Issues fixing cost | 10000
Testing Cost by Credit Card Company | 1000
Subscription Fees ( Assuming Botanic garden has 20,000 members and 1000 members registers every year) Kindly charges $100 for every 1000 members | 2000 | 2100 | 2200 | 2300 | 2400
Training Cost for Staffs (Assuming $60 training cost for each staff) | 1620
System Downtime Cost (while integration) | 4300
Interest Cost ( Assuming company take loan of $60,000 from bank @3% per annum for 4 years) |  | 936.75 | 936.75 | 936.75 | 936.75
Total Cost | 61920 | 7536.75 | 7636.75 | 7736.75 | 7836.75
Benefits
(Assuming Customers spending increases 1% each year in all facilities)
Gate and Membership credit card fees savings | 4080 | 4120.8 | 4162.008 | 4203.6281 | 4245.6644
Café credit card fees savings | 4263 | 4305.63 | 4348.6863 | 4392.1732 | 4436.0949
Store credit card fees savings | 4446 | 4490.46 | 4535.3646 | 4580.7182 | 4626.5254
Events credit card fees savings | 3630 | 3666.3 | 3702.963 | 3739.9926 | 3777.3926
Cost savings from office staff taking manual calls (40 hours per week) (Assusimg staffs are paid @$15/hour and it increases 3% annually) | 31200 | 32136 | 33100.08 | 34093.0824 | 35115.8749
Total Benefits | 47619 | 48719.19 | 49849.1019 | 51009.5945 | 52201.5521
ROI | 169.1%
Payback Year | 2